## Slide 1: NGS-Hap Project Work Report Start from July 7, 2019

## Slide 2: July 7, 2019 Meeting To-Do
1. Start a PowerPoint summary for each meeting (to do list + record of report) Complete, see July7.2019.ppt
2. Add detailed comments to Unix script Complete, see July7.RealDataDBM.txt
3. Output SNPs only (by adding “-v snps” to only view snps) bcftools view -v snps Complete, see July7.RealDataDBM.txt
4. (1) Convert the DBM input pipe to Perl code. Then compare the two by using “diff”. (2) Prepare DBM input using ≥6 coverage (DP≥6 or AD1+AD2≥6) for 826, 827, 832 on chr10 (3) Output the reference allele and alternative allele
In Progress, see /home/s_m774/project/data/dbm/7.7/prepare.pl

## Slide 3: July 14, 2019 Meeting To-Do
1. Find SNPs for 826 827 832 pair-end data with at least 4X coverage (DP>3)
In Progress, see bwaPairEnd.txt
2. Create and run a Perl script to get the DBM input (compare with the Unix script to make sure you have the same output)
Complete, see /home/s_m774/project/data/dbm/7.14/intersect/prepare.pl
3. (1) Run DBM on a single individual with 4X coverage
(2) Run DBM on 826 827 832 with 4X coverage
Complete, see July14.SingleDBM.txt
Complete, see July14.MultiDBM.txt
4. Prepare the DBM input and then run DBM on SNPs with at least 1X coverage on all individuals
Complete, see July14.IntersectDBM.txt

## Slide 4: July 21, 2019 Meeting To-Do
1. Find SNPs using pair-end data of 826, 827, 832. Then run DBM (chr10).
Complete, see July21.2019.PairEndDBM.txt
2. (1) Run HapSeq2 on sample data
(2) Prepare HapSeq2 input and then run HapSeq2 using real data 826, 827, 832
In progress, see July21.2019.HapSeq2BamParser.txt

## Slide 5: July 28, 2019 Meeting To-Do
Summarize all the work we have done so far
Complete, see slide #6
2. Prepare input on 5 PE individuals, ≥2X coverage, ≥3X samples on each position, and run DBM
Complete, see July28.2019.PairEndDBM
3. (1) Run HapSeq2 on sample data
(2) Prepare input using the 5 PE data, and run HapSeq2
In progress, see July28.2019.HapSeq2

## Slide 6: August 13, 2019 Meeting To-Do
1. (1) Correct the DBM 5 pick 3 task in Unix (2) Create a Perl script to prepare the same input then make sure they give the same results.
Complete, see August13.2019.PairEndDBM
Complete, see /home/s_m774/software/DBM/getStarfish.pl
2. (1) Prepare DBM input showing “ACGT” alleles
Complete, see August13.2019.AllelesDBM
3. Run Hapseq2 on sample data using 4 inputs (jump.txt and read.txt)
Complete, see August13.2019.HapSeq2
4. (1) Prepare Hapseq2 input using 3 samples (2) Run Hapseq2 using real data. First use 2 input files. Next use 4 input files.
In Progress

## Slide 7: August 13, 2019 Meeting To-Do
1. (1) Correct the DBM 5 pick 3 task in Unix (2) Create a Perl script to prepare the same input then make sure they give the same results.
Complete, see August13.2019.PairEndDBM
Complete, see /home/s_m774/software/DBM/getStarfish.pl
SS note on Aug 13, 2019: (1) set up the “MinNumSample” (not “depth”) in the argument (so we may change later)
2. Prepare DBM input showing “ACGT” alleles
Complete, see August13.2019.AllelesDBM
SS note on Aug 13, 2019: (1) samples have common chr.pos may have different alternative alleles (choose the one with larger alternative allele count) (2) for quality score, should use the average of more than one sample.
(3) using different names for different output files (not always 8256.pos)
3. Run Hapseq2 on sample data using 4 inputs (jump.txt and read.txt)
Complete, see August13.2019.HapSeq2
4. (1) Prepare Hapseq2 input using 3 samples (2) Run Hapseq2 using real data. First use 2 input files. Next use 4 input files.
In Progress (Continue to do)
New to do:
Check on the DBM and HapSeq2 paper and web page to (1) see if they have available simulation data and real data (2) check on the papers that cite these two papers to see if they have simulation data and real data
Next meeting time: Aug 21 Wed 2:30 pm

## Slide 8: August 13, 2019 Summary
Method | SNP count
Single End (3 samples) | 1714 (Union of 3 samples)
Single End, ≥4 coverage (3 samples) | 246 /home/s_m774/data/dbm/single.4depth.3sample/7.8
Single End, 3 pick 3 (3 samples) | 47 /home/s_m774/data/dbm/single.1depth.3sample/intersect
Pair End, ≥4 coverage (3 samples) | 417 /home/s_m774/data/dbm/pair.4depth.3sample/7.28
Pair End, ≥2 coverage, 5 pick 3 | 120 /home/s_m774/data/dbm/pair.2depth.5sample/8.10 - Starfish

## Slide 9: Aug 13, 2019 notes during the meeting for positions with more than 1 alternative alleles.
For position with more than 1 alternative alleles, so far we delete/exclude them (because only 1 or 2 positions for each sample) , see “August13.2019.AllelesDBM.txt”
/home/s_m774/data/dbm/pair.2depth.5sample/allele.8.11
grep ^chr10 826.vcf | cut -f 1,2,4,5,6,10 | sed s/:/\\t/g | awk '{print $1"\t"$2"\t"$9"\t"$3"\t"$4"\t"$5}' | sed s/,/\\t/g | awk 'NF == 7' > 826.pos
grep ^chr10 827.vcf | cut -f 1,2,4,5,6,10 | sed s/:/\\t/g | awk '{print $1"\t"$2"\t"$9"\t"$3"\t"$4"\t"$5}' | sed s/,/\\t/g | awk 'NF == 7' > 827.pos
grep ^chr10 832.vcf | cut -f 1,2,4,5,6,10 | sed s/:/\\t/g | awk '{print $1"\t"$2"\t"$9"\t"$3"\t"$4"\t"$5}' | sed s/,/\\t/g | awk 'NF == 7' > 832.pos
grep ^chr10 826.vcf | cut -f 1,2,4,5,6,10 | sed s/:/\\t/g | awk '{print $1"\t"$2"\t"$9"\t"$3"\t"$4"\t"$5}' | sed s/,/\\t/g | awk 'NF != 7' > 826.multiple
grep ^chr10 827.vcf | cut -f 1,2,4,5,6,10 | sed s/:/\\t/g | awk '{print $1"\t"$2"\t"$9"\t"$3"\t"$4"\t"$5}' | sed s/,/\\t/g | awk 'NF != 7' > 827.multiple
grep ^chr10 832.vcf | cut -f 1,2,4,5,6,10 | sed s/:/\\t/g | awk '{print $1"\t"$2"\t"$9"\t"$3"\t"$4"\t"$5}' | sed s/,/\\t/g | awk 'NF != 7' > 832.multiple
# SNP counts at ≥2 coverage, pair end
wc -l *.pos
354 826.pos
504 827.pos
791 832.pos
wc -l *.multiple
1 826.multiple
1 827.multiple
2 832.multiple
[s_s355@login1 allele.8.11]$ grep 19438631 826.vcf
chr10 19438631 . A G,T 29.769 . DP=3;VDB=0.0221621;SGB=-0.511536;MQ0F=0;AF1=1;AC1=2;DP4=0,0,0,3;MQ=60;FQ=-32.988 GT:PL:DP:AD1/1:72,17,11,60,0,57:3:0,2,1
[s_s355@login1 allele.8.11]$ grep 127016760 827.vcf
chr10 127016760 . T C,A 12.0443 . DP=3;VDB=0.0221621;SGB=-0.511536;MQ0F=0;AF1=1;AC1=2;DP4=0,0,0,3;MQ=29;FQ=-32.9882 GT:PL:DP:AD1/1:53,16,10,42,0,39:3:0,2,1
[s_s355@login1 allele.8.11]$ grep 41879457 832.vcf
chr10 41879457 . C G,A 19.314 . DP=6;VDB=0.0112566;SGB=-0.616816;MQSB=1;MQ0F=0;AF1=1;AC1=2;DP4=0,0,1,5;MQ=20;FQ=-41.9862 GT:PL:DP:AD 1/1:63,26,11,45,0,42:6:0,5,1
[s_s355@login1 allele.8.11]$
[s_s355@login1 allele.8.11]$ grep 133247608 832.vcf
chr10 133247608 . C T,G 34.9733 . DP=4;VDB=0.225386;SGB=-0.556411;MQSB=1;MQ0F=0;AF1=1;AC1=2;DP4=0,0,3,1;MQ=60;FQ=-35.9869 GT:PL:DP:AD1/1:69,11,2,64,0,61:4:0,3,1

## Slide 10: August 23, 2019 Meeting To-Do
1. Set up “MinNumSample” (not “depth”) as an argument in the DBM Perl script (so we may change it later)
Complete, see /home/s_m774/software/DBM/perl/get5SampleKey.pl
2. (1) Choose the larger alternative allele count in samples with the same chr.pos and different alternative alleles (2) Add real quality scores to the DBM input (3) Calculate average quality score of multiple samples
In Progress, see August23.2019.AllelesDBM (To finish)
Complete, see August23.2019.QualityScoreDBM
In Progress, see August23.2019.QualityScoreDBM (To finish)
3. (1) Prepare Hapseq2 real data with 3 samples (2) Run Hapseq2 using real data. First use 2 input files. Next use 4 input files.
In Progress, see August23.2019.HapSeq2RealData (To finish)
4. (1) Check on the DBM and HapSeq2 paper and web page to see if they have available simulation data and real data (2) Check on the papers that cite these two papers to see if they have simulation data and real data.
Complete, see August23.2019.Data
(SS note on Aug 23, 2019 Friday: Check journal web for supple files and software webpage, did not find DBM and HapSeq simultation data, may contact the authors to ask later if necessary)

## Slide 11: August 30, 2019 Meeting To-Do
1. Choose the larger alternative allele count in samples with the same SNP and different alternative alleles
Complete, see August30.2019.AllelesDBM.txt
2. Calculate average quality score of multiple samples
Complete, see August30.2019.QualityScoreDBM.txt (to be revised)
Aug 30, 2019 Friday SS notes: the above code is only for 2 samples. Should revise it for 5 or more samples. Generate two output files, one is the “final” output like the one generated by the above code, another is the middle step output, see below.
Chr pos s1.quality s2.quality s3. quality s4.quality s5.quality
Chr10 127 NA NA 70 61 80
Chr10 350 33 24 NA 12 NA
…
3. (1) Prepare Hapseq2 real data (2) Run Hapseq2 using real data. First use 2 input files. Next use 4 input files. (3) Prepare Hapseq2 real data with 3 samples
In Progress (continue to finish)
4. Check on the papers that cite the DBM and HapSeq2 papers to see if they have simulation data and real data.
In Progress (continue to finish)

## Slide 12: September 5, 2019 Meeting To-Do
1. (1) Get the quality scores of each SNP on each sample (2) Calculate average quality score of 5 samples
Complete, see September5.2019.QualityScoreDBM.txt
2. (1) Prepare Hapseq2 real data (2) Run Hapseq2 using real data. First use 2 input files. Next use 4 input files. (3) Prepare Hapseq2 real data with 3 samples
In Progress, see September5.2019.HapSeq2Input.txt (continued to do)
3. Check on the papers that cite the DBM and HapSeq2 papers to see if they have simulation data and real data.
In Progress
Web links for papers that have the figures listed on the next page:
1. Figure 1: https://biodatamining.biomedcentral.com/articles/10.1186/s13040-019-0198-8
2. Figure 2 https://www.ncbi.nlm.nih.gov/pmc/articles/PMC4530977/

## Slide 13: Examples of work flow
Summary of running DBM:
work flow (better to include code, input and output): from raw data to DBM output
1 ~2 paragraph of preparing DBM input and running DBM (words)
Have a code summary (explain what each code really does)
 this can be part if the work flow. That is 1) and 3) can be combined.
Code summary example: Code.Summary.Aug9.2019.by.Jas.txt under this folder on TRACS
2.Hap.May.2018 Resources/ 6.Files.for.Sherwin

## Slide 14: September 12, 2019 Meeting

## Slide 15: September 12, 2019 Meeting To-Do
1. (1) Prepare Hapseq2 real data (2) Run Hapseq2 using real data. First use 2 input files. Next use 4 input files. (3) Prepare Hapseq2 real data with 5 samples
In Progress, see September12.2019.HapSeq2Memory
2. (1) Summarize running DBM from raw data to DBM output with a workflow (code, input, and output) (2) Write 1 to 2 paragraphs on preparing DBM input and running DBM (3) Create a code summary explaining what each code does
In Progress, (1) (2)
Complete, see September5.2019.DBMCodes.txt
3. Check on the papers that cite the DBM and HapSeq2 papers to see if they have simulation data and real data.
Complete, see September12.2019.DataSet.txt
Sept 13, 2019 SS Meeting notes:
About Bam And Indexed Bam Files: https://www.biostars.org/p/15847/
Haplotype assembly output of 4 software packages, see the next page (from Bertie’s slide page 18)

## Slide 16
# PEATH output, the last hpalotype block (VCF 803-807) is different from HapCUT2, HapCompass, and MixSIH
/home/abj15/Research.Project/Run/PEATH/7.15.2019_826T_chr10.PE
more 826T_chr10_PEATH_haplotype.txt
Block Number: 1 Block Length: 2 Phased Length: 2 Number of R
Block Number: 12 Block Length: 5 Phased Length: 5 Number of Reads: 4 Start position: 803 Weighte
d MEC: 2.01657 MEC: 2
803 0 1
804 0 1
805 1 0
806 1 0
807 1 0
*******
/home/abj15/Research.Project/Run/HapCompass/7.13.2019_826T_chr10.PE
tail 826T_chr10.PE.haplotype.output_MWER_solution.txt
BLOCK 132858318 132858392 158 162 22.0 chr10
VAR_POS_132858318 132858318 158 0 1
VAR_POS_132858336 132858336 159 0 1
VAR_POS_132858370 132858370 160 0 1
VAR_POS_132858380 132858380 161 0 1
VAR_POS_132858392 132858392 162 0 1
/home/abj15/Research.Project/Run/HapCUT2/7.13.2019_826T_chr10.PE
# HapCut2 output: 826T_chr10.PE.haplotype.file
BLOCK: offset: 803 len: 5 phased: 5 SPAN: 74 fragments 4
803 1 0 chr10 132858318 T G 0/1:99,0,12 0. 65.61
804 1 0 chr10 132858336 T C 0/1:50,0,38 0. 65.61
805 1 0 chr10 132858370 C T 0/1:38,0,30 0. 100.00
806 1 0 chr10 132858380 T A 0/1:44,0,16 0. 100.00
1 0 chr10 132858392 G T 0/1:40,0,43
/home/abj15/Research.Project/Run/MixSIH/7.15.2019.826T_chr10.PE
tail 826T_chr10.PE.haplotype.txt
BLOCK: offset: 803 len: 5 phased: 5
803 1 0
804 1 0
805 1 0
806 1 0
807 1 0
********

## Slide 17
Software: BWA
Input: FASTA reads
Output: SAM format
Software: Samtools 1.9
Input: SAM format
Output: BAM format
Software: Bcftools 1.9
Input: BAM format
Output: VCF file with SNPs
Software: Get5SampleKey.pl
Input: VCF file with SNPs
Output: sample.snps
Software: DBM
Input: SNP file and counts file
Output: sample.g
Software: GetCounts.pl
Input: SNP file and VCF file
Output: sample.counts

## Slide 18: DBM Pipeline
Five samples of pair end fastq reads were alligned to the HG38 human reference genome using BWA. Step 1 is to align the reads using aln (Options -I to specify Illumina 1.3+ and -t to specify thread count were used). Step 2 is to convert the pair end reads to the sam format using sampe (-P to load index to memory for better preformance was used). The mapped reads were converted from sam to bam and sorted using samtools 1.9. Step 1 is to view the reads in bam format using view (-b specified bam output and -o specified the output file). Step 2 is to sort the bam file (-o specified the output file).
The sorted bam file is then searched for SNPs using bcftools 1.9. Step 1 is to use mpileup to find variants (-I Indels are skipped, -g Genotype to BCF output, -a AD annotate Allele Depth, -a DP annotate Depth, -f FASTA format index). Step 2 is to filter the variants for quality using view (-i include only if above minimum depth). Step 3 is to search the vcf file for SNPs using call (-c consensus caller, -v variant sites only output, -o output file.) Next the two DBM input files sample.snps and sample.counts are prepared using the vcf file containing the SNPs. These input files are generated using the perl scripts get5SampleKey.pl and getCount.pl, and the DBM header is inserted into the counts file using the Unix command sed. DBM was ran by specifying the prefix of the two input files sample.snps and sample.counts ('sample' in this case) and the haplotype file sample.g is generated.
D CHR POS I1 I1 I2 I2 I3 I3
0 chr10 48086 0 1 1 0 1 1
1 chr10 789566 1 0 0 1 0 1
2 chr10 1182970 1 1 1 0 0 1
3 chr10 1183069 0 1 0 1 1 1

## Slide 19: September 19, 2019 Meeting

## Slide 20: September 19, 2019 Meeting To-Do
1. (1) Prepare Hapseq2 input using real data (2) Run Hapseq2 using real data
(3) Prepare Hapseq2 input using 5 samples
In Progress, see September19.2019.HapSeq2BamParser.txt
2. (1) Create a workflow for running DBM from raw data to DBM output
(2) Write 1 to 2 paragraphs on preparing DBM input and running DBM
(1) In Progress (2) Complete, see Slide 16
3. Create a Perl script to format PEATH Haplotype assembly output
Complete, see September19 PerlFormat.txt
4. Create a Perl script to format HapCompass Haplotype assembly output
Complete, see September19 PerlFormat.txt
5. Create a Perl script to format HapCut2 Haplotype assembly output
Complete, see September19 PerlFormat.txt

## Slide 21: September 28, 2019 Meeting

## Slide 22: September 28, 2019 Meeting To-Do
1. (1) Prepare Hapseq2 input using real data (2) Run Hapseq2 using real data
(3) Prepare Hapseq2 input using 5 samples
In Progress, see September26 2019 HapSeq2RealData.txt
Documented error when running HapSeq2 in the last 5 lines
2. Create a workflow for running DBM from raw data to DBM output
Complete, see Slide 16
3. Update the Perl scripts for PEATH HapCompass Hapcut2 to count Haplotypes
Complete, see September26 2019 PerlFormat.txt

## Slide 23
SS note on Sept 28, 2019 Saturday. The error related to the hapseq running error “Person 1 is
Duplicated” (in September26 2019 HapSeq2RealData.txt)
because the first 5 columns (family ID, individual ID, father, mother ID, and gender)
Are not provided correctly because we run part of the bam.parser code sample by sample. See below
We should either manually fix the ”ID” or add “sample ID” as one of the parameters, e.g.,
./bam_parser BAMs/8212ch10.bam chr10wchr.vcf parsed/826chr10 1
# The incorrect one:
> count[1:5, 1:20]
V1 V2 V3 V4 V5 V6 V7 V8 V9 V10 V11 V12 V13 V14 V15 V16 V17 V18 V19 V20
1 1 1 0 0 1 1 1 39 19 0 24 0 42 14 15 0 23 0 138 0
2 1 1 0 0 1 0 0 59 3 26 4 31 6 24 0 0 21 0 118 0
3 1 1 0 0 1 0 2 1 143 20 0 47 25 45 0 0 84 163 201 0
4 1 1 0 0 1 0 0 44 0 21 0 23 0 12 8 0 14 1 157 0
1 1 0 0 1 1 2 52 65 0 25 0 90 20 20 0 57 1 246 111
# The correct one:
> count<-read.table("count.txt", header=F)
> count[1:5, 1:20]
V1 V2 V3 V4 V5 V6 V7 V8 V9 V10 V11 V12 V13 V14 V15 V16 V17 V18 V19 V20
1 1 1 0 0 1 1 1 39 19 0 24 0 42 14 15 0 23 0 138 0
2 2 2 0 0 1 0 0 59 3 26 4 31 6 24 0 0 21 0 118 0
3 3 3 0 0 1 0 2 1 143 20 0 47 25 45 0 0 84 163 201 0
4 4 4 0 0 1 0 0 44 0 21 0 23 0 12 8 0 14 1 157 0
5 5 5 0 0 1 1 2 52 65 0 25 0 90 20 20 0 57 1 246 111

## Slide 24: Sept 28, 2019 Saturday meeting notes
ASHG: Oct 15 T - Oct 17 . Math Open House: Nov 8 Friday
Get the poster ready Oct 8 T or Oct 9 Wed:
# Hapseq2 /home/s_m774/data/hapseq2/testrun/sample.haplotype.txt
# DBM: /home/s_m774/data/dbm/pair.2depth.5sample/5sampleDBM.9.28
# These two files are copied to /home/s_m774/data/compare/
HapSeq2
tttggcatgt
cctgacatgc
DBM
ID CHR POS I1 I1
1 chr10 1183608 T T 0 0.5
2 chr10 1185028 T C 1 1
3 chr10 1199953 T A 0 0.5
4 chr10 1233561 T G 0 0.5
5 chr10 1737155 G A 1 1
6 chr10 3010999 C A 0 0.5
7 chr10 3011174 A A 1 1
8 chr10 5073699 T G 0 0.5
9 chr10 5073715 G T 1 0.5
10 chr10 8644132 T C 1 1
"strict" genotype comparison: 5/10 agreement
"not strict" genotype comparision: 7.5/10
output this person by person:
strict compare: 65/120 for sample826 70/120 for sample827 ....
Not strict compare: 80/120 for sample826 95/120 for sample827 ....

## Slide 25: October 3, 2019 Meeting

## Slide 26: October 3, 2019 Meeting To-Do
1. Create a standard format for genotype data to compare DBM and HapSeq2 genotype data
Complete, see October3 2019 CompareHapSeq2DBM.txt
2. Create code to count the genotype agreement of the DBM and HapSeq2 results using strict pointing
Complete, see /home/s_m774/software/perl/getPoints.pl
I will be a co-author of this poster:

## Slide 27: October 3, 2019 Meeting To-Do V2
1. Find genotype agreement of the DBM and HapSeq2 results using (1) strict pointing and (2) non-strict pointing
Complete, see October3 2019 Updated Genotype Agreement.txt
# 826
Strict genotype agreement: 49/120
Non-Strict genotype agreement: 83.5/120Job took 0 seconds
# 827
Strict genotype agreement: 48/120
Non-Strict genotype agreement: 81.5/120Job took 0 seconds
# 832Strict genotype agreement: 60/120Non-Strict genotype agreement: 88.5/120Job took 0 seconds# 847Strict genotype agreement: 45/120Non-Strict genotype agreement: 78/120Job took 0 seconds# 850Strict genotype agreement: 62/120Non-Strict genotype agreement: 87.5/120Job took 0 seconds

## Slide 28: DBM and HapSeq2 Genotype Comparison
# 826
Strict genotype agreement: 49/120
Non-Strict genotype agreement: 83.5/120
# 827
Strict genotype agreement: 48/120
Non-Strict genotype agreement: 81.5/120
# 832
Strict genotype agreement: 60/120
Non-Strict genotype agreement: 88.5/120
# 847
Strict genotype agreement: 45/120
Non-Strict genotype agreement: 78/120
# 850
Strict genotype agreement: 62/120
Non-Strict genotype agreement: 87.5/120

## Slide 29: October 10, 2019 Meeting

## Slide 30: October 10, 2019 Meeting To-Do
1. Create code to find haplotype block conflicts in hapcut2 and PEATH haplotype files
Complete, see /home/s_m774/software/perl/getHapcutPeathConflicts.pl
2. (1) Create test cases for the code (2) Run on full hapcut2 and PEATH haplotype file created by Dr. Sun
Complete, see October10 2019 CompareHapCut2PEATH.txt

## Slide 31: October 10, 2019 Results
Directory: /home/s_m774/data/compare/peathHapCut
1012/31355 (3.23%): Hapcut and Peath disagree with each other on 1012 out of 31355 Peath blocks.
cut -f 5 fullResult.txt | sort | uniq | wc -l
1012
cut -f 5 hapcutPeath.2019.10.3.txt | sort | uniq | wc -l
31355
4875/115813 (4.21%): HapCut and Peath disagree with each other on 4875 out of the total 115813 SNVs.
Wc –l
4875 fullResult.txt
115813 hapcutPeath.2019.10.3.txt

## Slide 32: October 22, 2019 Meeting

## Slide 33: October 22, 2019 Meeting To-Do
1. Create a list of more MIHA software packages
In Progress, see October21 2019 MIHA
2. Search for real data with a known truth and simulation data
Complete, Models.zip is provided by GenHap
A. The two files in the root are real data
B. The directories contain simulated input data with their known truth (ground truth) as a txt file with the same name
3. Create a Perl code to compare the 3 SIHA algorithms: Peath, HapCUT2, and mixSIH
In Progress, this task needs refinement

## Slide 34
Create a list of more MIHA software packages
(1) check the papers that cited DBM and HapSeq2 to see which software DBM and HapSeq2 have been compared with
(2) based on the excels from Bertie
(3) Just simply Google

## Slide 35
Create code to compare the 3 SIHA algorithms: Peath, HapCUT2, and mixSIH
1. Which blocks have all 3 agree, 2 agree, and 0 agree
Note: I can output the agreement of software packages being either
A. 3 way
B. Disagreement exists
2. Select one input’s block ID to output the 12 columns of the input file
+ # of HA agreement 3, 2, or 0
+ two haplotypes preferred 000, 111, with the reference allele "0" on the left

## Slide 36: November 7, 2019 Meeting

## Slide 37: November 7, 2019 Meeting To-Do
1. Create a Perl code to compare the 3 SIHA algorithms: Peath, HapCUT2, and mixSIH
Complete, see getAgreement12Col Peath HapCut2 MixSIH 2019.11.7
2. Check these papers for MIHA software packages:
HAPI-UR, 2012
MaCH, 2010
BEAGLE, 2007
In Progress