## Slide 1: NGS-Hap Project Work Report Start from June 27, 2019

## Slide 2: Key files or work summary
See: Key_files_work_summary.July16.2019

## Slide 3: June 27, 2019 Meeting To-Do
0. Checking “extractHAIRS” output (fragment file), see “June27.2019.extracthairs.docx “
Mannual website, issue 40: https://github.com/vibansal/HapCUT2/issues/40
Answer: Done.
*see slide 4 for details
1. Use a PPT file to summarize each to-do task
Answer: Done. We start to to provide a work report, see “June27.2019.work.report.pptx”.
2. Summarize the Althap input regarding put the number of reads and number of columns
Answer: Done.
3. For 826T sample, only 1 mate (not using the pair-end data). Extract one chromosome (e.g., chr10) from a sam file, then convert to bam, see this web page:
https://carleshf87.wordpress.com/2013/10/28/extracting-reads-for-a-single-chromosome-from-bamsam-file-with-samtools/
Chr10.fa file: /group/hon/hon3398o/0.course.files/Data/Reference/hg38/chroms/chr10.fa
Previous alignment script file: Datasets.june9.2019.txt
Answer: Done.
Alignment script: 826T_1_sequence.chr10.Alignment.July1.2019
*see slide 5 for description
4. For the previous software that works for the real data, go back to run just on one chromosome (chr10)
HapCompass, HapCUT, HapCUT2, AltHap, MixSIH
Answer: Done: HapCompass, HapCUT, HapCUT2, MixSIH & AltHap
*See slide 6 for details
5. Althap: Only extract the reads on chr10 in this region: 125737910 +/- 500 or 1000 or 2000 bases
Extract reads for a specific chromosome region: https://www.biostars.org/p/48719/
Answer: Done, see 826T_1_sequence.chr10.Alignment.July1.2019 & AltHap.Input.826T_1_chr10.July1.2019
*see slide 7 for details
6. MixSIH & CSP: what we have done, what to do next, why did we stop our discussion on Thursday 6/27/2019
Answer: Done
*see slide 8 for details
7. List of software packages that infer haplotypes for more than 1 sample.
Answer: DBM, HapSeq2
*see slide 9 for details

## Slide 4: Checking “extractHAIRS” output (fragment file)
HapCUT: No description of fragment file format created by the extractHAIRS command
HapCUT2: Author’s description for fragment file format
  Mannual website: https://github.com/vibansal/HapCUT2/issues/40
  In the hapcut input file, each line has haplotype information from a single fragment. For each variant covered by the fragment, information about the variant-id and allele is recorded as follows:
  Column 1 is the number of blocks (consecutive set of variants covered by the fragment). Column 2 is the fragment id. Column 3 is the offset of the first block of variants covered by the fragment followed by the alleles at the variants in this block. Column 5 is the offset of the second block of variants covered by the fragment followed by the alleles at the variants in this block. ...
  The last column is a string with the quality values (Sanger fastq format) for all the alleles covered by the fragment (concatenated for all blocks).
  For example, if a read/fragment covers SNPs 2,3 and 5 with the alleles 0, 1 and 0 respectively, then the fragment will be:
  2 read_id 2 01 5 0 AAC
MixSIH: Use fragment file created from HapCUT2’s extractHAIRS command to generate needed input file.
  Mannual websit: https://github.com/hmatsu1226/MixSIH
  Format of Input_file
    First line : Describes the number of lines of Input_file (which corresponds to the number of SNP fragments - 1).
    After first line : Each line describes a SNP fragment as below.
      \segment_num \fragment_name \start_site1 \sequence1 \start_site2 \sequence2.....
      \segment_num : The number of the segments which don't have gaps in the segments.
      \fragment_name : The name of the fragment.
      \start_allele'i' : The first site's position of i-th segment (1-origin).
      \sequence'i' : The sequence of i-th segment.
    The fragments must be sorted by the value of the third column and these can be sorted as follows: sort -n -k 3 frag.txt > frag_sorted.txt
AltHap: Use extractHAIRS to generate main component of input fragment file
  Mannual website: https://github.com/realabolfazl/AltHap
    The input file format is as follows
    Number of reads Number of columns Number_of_contiguos_segments Read_identifier Position_of_first_SNP_segment Continuous_bases_in_read Position_of_next_SNP_segment Continuous_bases_in_read ..... Quality_scores (in fastq format)
    Example for Biallelic:
    5568 22801 2 chr22_SPA9_8733 2 0 5 0 == 1 chr22_SPH2_1940 3 100 C==
sort -n -k 3 frag.txt > frag_sorted.txt

## Slide 5: 4. For 826T sample, only 1 mate (not using the pair-end data). Extract one chromosome (e.g., chr10) from a sam file, then convert to bam
Alignment script: 826T_1_sequence.chr10.Alignment.July1.2019:
Contains the alignment scripts for aligning the mate end dataset 826T_1.
This full dataset was aligned via bwa, converted into a .sam file, .bam file & indexed .bai file via samtools. Samtools was used to extract chr10 only from the 826T_1 dataset.
Then bcftools was used to convert the sorted .bam file to a .bcf file and then ultimately a .vcf file.
Lastly, bam and vcf files were created for chromosome positions centered around position “125737910” ( the position possible correlated to position “480” in extracHAIRS), varying plus and minus 500, 1000 & 2000 bases.

## Slide 6: 5. For the previous software that works for the real data, go back to run just on one chromosome (chr10)
Text Files:
  AltHap.Input.826T_1_chr10.July1.2019
  HapCompass.826T_1_chr10.July1.2019
  HapCUT.826T_1_chr10.July1.2019
  HapCUT2.826T_1_chr10.July1.2019
  MixSIH.826T_1_chr10.July1.2019

## Slide 7: 6. Althap: Only extract the reads on chr10 in this region: 125737910 +/- 500 or 1000 or 2000 bases
AltHap.Input.826T_1_chr10.July1.2019
  The first step before running AltHap on the 3 datasets for 826T_1_chr10 with ranges of 1000, 2000 & 4000 bases center around chromosome position “125737910” is to run HapCUT2’s extractHAIRS command on each pair of bam & vcf files.
  extractHAIRS generated fragment files for each range set that had no content.

## Slide 8: MixSIH & CSP: Update
MixSIH: success fully ran on real data, see file MixSIH.826TRealData.June16.2019 & MixSIH.826T_1_chr10.July1.2019
CSP: Success running example script, however output for real data is empty.
  See: CSP.826TRealData.June19.2019

## Slide 9: Software Packages that infer haplotypes for more than one sample
DBM
HapSeq2

## Slide 10: July 2, 2019 Meeting To-Do
Make a file for all key files (listed on July 2 meeting PPT file)
  Answer: Done: See zipfile ‘1.Key_Files.July9.2019’
Run whole pair-end data (826) for all the software packages that use the same/similar "fragment" input file, which is obtained based on extractHairs: HapCUT2, HapCompass, MiXSIH, AltHAP, Sdhap &PEATH
  Answer: Done: HapCompass, HapCUT2, AltHap, MixSIH,
  Unsuccessful Runs: Sdhap (Real data)& & PEATH (issues compiling PEATH.cpp file)
CSP run on a real data
  Answer: Unsuccessfully ran on real data: whole pair-end 826T data
  Attempted 4 separate runs, see CSP_pairend_826T.July9.2019
The common data used: NA12878? Fosmid_all_chromosomes? (1) Check if NA12878 and Fosmid_all_chromosomes are the same (2) SDHAP web page has the both real data and simultation data https://sourceforge.net/projects/sdhap/files/ (3) Check other software packages' web page to see if they provide any simulated or real data
  Answer: Done:
  Real data info from MixSIH, PEATH, GenHap, SDhaP, IMPUTE2 & HapCol
  *See details on page 11 & 12
  NA12878: dataset website link and description on page 13
Create a word doc of input and output format for software packages
  Answer: Done: HA_software_package_input.output_formats

## Slide 11: HA software Packages: Real & Simulated Datasets
GenHap:
  (i) the chromosome 22 of the individual NA12878 obtained starting from high-quality SNP calls and sequencing data made publicly available by the Genome in a Bottle (GIAB) Consortium
  (ii) the chromosome 22 obtained starting from PacBio data.
  Simulated data: located under the Models/Freq_100 directory
IMPUTE2: https://mathgen.stats.ox.ac.uk/impute/impute_v2.html#reference
  Above link provides links to:
    9 different 10000 genome project links
    4 different HapMap phases
HapSeq2:
  Simulated data: located in the zip file of HapSeq2 under the HapSeq2_pipeline directory: BAMs: directory, CEU.sample.ID.txt & sites.vcf
ParticleHap:
  Simulated data: located in the zip file of ParticleHap, testdata.txt
HapCol: https://github.com/AlgoLab/HapCol/tree/master/data/real
  ‘input-duitama’: contains sorted matrices for each chromosome & WIF formatted input (same as GenHap input)
  ‘haplotype-duitama’: contains refhap phase files for each chromosome
  Simulated data: located under the data/simulated directory of the zip file
HapCompass:
  Simulated date: located under the example directory of the HapCompass zip file: 62_ID0.txt & example.bam
HapCUT:
  NA12878: located under testdata directory in zip file of HapCUT: HapCUT/hapcut-master/testdata/
  fosmiddata.chr20.fragments, fragment_matrix_file, NA12878.chr20.1KG.vcf, NA18508.chr20.test.bam & NA18508.chr20.test.VCF

## Slide 12: HA software Packages: Real & Simulated Datasets
MixSIH:
  For real data, we used the SNP fragments of Duitama's group [1] and it was downloaded from http://owww.molgen.mpg.de/~genetic-variation/SIH/data/ .
  As the correct haplotypes, we used the haplotypes which are determined by pedigree genotypes and we downloaded these from 1000 Genomes Project: ftp://ftp.1000genomes.ebi.ac.uk/vol1/ftp/pilot_data/release/2010_07/trio/snps/CEU.trio.2010_03.genotypes.vcf.gz
  Simulated data: frag_sample.txt located in zip file of software
CSP:
  Simulated data: fragment.txt & genotype.txt, located in zip file under example directory
PEATH:
  We used three data sets for experiments.
    Fosmid dataset (Duitama et al. 2012) which has been widely used to assess and compare SIH algorithms.
    Simulated dataset which was generated based on Fosmid data.
    HuRef dataset (Levy et al. 2007) which has been the most widely used in SIH related articles.
    Simulated data: located in the zip file of PEATH, under the DataSet/Simulated_chromosomes/ directory, 60 .matrix.SORTED files
SDhaP: https://sourceforge.net/projects/sdhap/files/
  Fosmid data (zipfile): sorted matrices
  HuRef data (zipfile)
  Simulated data (zip file)
AltHap:
  Simulated data: located under the zip file for AltHap: sim0.txt

## Slide 13: NA12878: HapMap trio child
Website of full details on dataset: http://www.internationalgenome.org/data-portal/sample/NA12878
“Fosmid-based whole genome haplotyping of a HapMap trio child: evaluation of Single Individual Haplotyping techniques” by: Duitama, Jorge, et al. https://www.ncbi.nlm.nih.gov/pmc/articles/PMC3299995/
  Most commonly referenced paper for real data among HA software packages
  Abstract description of NA12878 dataset:
    “we generated whole genome fosmid sequence data from a HapMap trio child, NA12878, for which reliable haplotypes have already been produced… We expanded the haplotypes for NA12878 by combining the current haplotypes with our fosmid-based haplotypes, producing near-to-complete new gold-standard haplotypes containing almost 98% of heterozygous SNPs. This improvement includes notable fractions of disease-related and GWA SNPs.”

## Slide 14: July 9, 2019 Meeting To-Do
Align pair-end dataset 826T chr10 & run on: MixSIH, CSP, PEATH, SDhaP, AltHap, HapCUT2 & HapCompass.
  Answer:Done.
  Alignment script: Alignment_826T_chr10_PE_July16.2019
  MixSIH script: MixSIH_826T_chr10_PE.July16.2019
  CSP script: CSP_826T_chr10_PE.July16.2019
  AltHap script: AltHap_826T_chr10_PE.July16.2019
  HapCUT2 script: HapCUT2_826T_chr10_PE.July16.2019
  HapCompass script: HapCompass_826T_chr10_PE.July16.2019
  PEATH script: PEATH_826T_chr10_PE.July16.2019
  SDhaP script: SDhap_826T_chr10_PE.July16.2019
Compare HapCUT2 & Hapcompass’ output ran on PE 826T chr10 dataset with output ran on SE 826T chr10 dataset.
  Answer:Done.
  HapCUT2: HapCUT2_Comparison_826T_chr10_SEandPE.July16.2019
  HapCompass: HapCompass_Comparison_826T_chr10_SEandPE.July16.2019
Correct Real data runs for MixSIH & CSP: create fragment files that list all variants.
  Answer: Done.
  MixSIH: MixSIH_corrections_826T.PE_and_1mil.826T.PE.July16.2019
  CSP: CSP_corrected.frag.files_826T.PE_and_1mil.826T.PE.July16.2019
Dig deeper into Real Datasets & NA12878: search for fastq file
  Answer: Done
  *see details page 15 & 16
Update Key_Files & maintain/organize file.
  Answer: Done
  Organized Run directory, now contains dates and details of what was one in each software packages’ subdirectory.
Add more to input/output format word doc.
  Answer: Done: HA_s.package_input.outputs.July16.2019
Update Software.Packages.June27.2019
  Answer: Done

## Slide 15: NA12878 dataset
Official website: https://www.internationalgenome.org/data-portal/sample/NA12878

## Slide 16: NA12878 dataset
The Genome in a Bottle Consortium:
  https://github.com/genome-in-a-bottle
  ftp://ftp-trace.ncbi.nlm.nih.gov/giab/ftp/data/NA12878/NIST_NA12878_HG001_HiSeq_300x
The Genome in a Bottle Consortium: materials & data: https://jimb.stanford.edu/giab-resources
  High-confidence variant calls: ftp://ftp-trace.ncbi.nlm.nih.gov/giab/ftp/release/NA12878_HG001/
  We have also uploaded fastq and bam files from ~300x total coverage of 150x150bp HiSeq2500 sequencing of NA12878/HG001 to: ftp://ftp-trace.ncbi.nlm.nih.gov/giab/ftp/data/NA12878/NIST_NA12878_HG001_HiSeq_300x
Which datasets should I use for reviewing or benchmarking purposes?
  https://gatkforums.broadinstitute.org/gatk/discussion/1292/which-datasets-should-i-use-for-reviewing-or-benchmarking-purposes

## Slide 17: July 16, 2019 summary of comparing a few software packages
Obvious: PE data of the same smaple give more haplotyes than the SE data
HapCUT2 and HapCompass run on all-chr-then-extract-chr10 and only run on chr10 will give the same results.
When compare hapCUT2, hapCompass, misSIX, and PEATH, we found they are same/smilar except the following :
(1) if we do not consider the relationships of different blocks (i.e., if they are from the same parent(Father or mother), HapCUT2, hapComapss, MisSIH give the same results.
(2) PEAT has one block that is different from others, a switch is needed to get the same results, see the next page
(3) For AltHap, there is no clear information on the haplotype’s chromsome position
VCF position in different output files, 803 means the 803th SNVs in the VCF file (with on header)
BLOCK: offset: 803 len: 5 phased: 5 SPAN: 74 fragments 4
803 1 0 chr10 132858318 T G
804 1 0 chr10 132858336 T C
805 1 0 chr10 132858370 C T
806 1 0 chr10 132858380 T A
807 1 0 chr10 132858392 G T

## Slide 18
#######################################
# PEATH output, the last hpalotype block (VCF 803-807) is different from HapCUT2, HapCaompass, and MixSIH
/home/abj15/Research.Project/Run/PEATH/7.15.2019_826T_chr10.PE
more 826T_chr10_PEATH_haplotype.txt
Block Number: 1 Block Length: 2 Phased Length: 2 Number of R
Block Number: 12 Block Length: 5 Phased Length: 5 Number of Reads: 4 Start position: 803 Weighte
d MEC: 2.01657 MEC: 2
803 0 1
804 0 1
805 1 0
806 1 0
807 1 0
*******
# HapCompass
[s_s355@login2 7.13.2019_826T_chr10.PE]$ pwd
/home/abj15/Research.Project/Run/HapCompass/7.13.2019_826T_chr10.PE
[s_s355@login2 7.13.2019_826T_chr10.PE]$ tail 826T_chr10.PE.haplotype.output_MWER_solution.txt
BLOCK 132858318 132858392 158 162 22.0 chr10
VAR_POS_132858318 132858318 158 0 1
VAR_POS_132858336 132858336 159 0 1
VAR_POS_132858370 132858370 160 0 1
VAR_POS_132858380 132858380 161 0 1
VAR_POS_132858392 132858392 162 0 1
/home/abj15/Research.Project/Run/MixSIH/7.15.2019.826T_chr10.PE
[s_s355@login2 7.15.2019.826T_chr10.PE]$ tail 826T_chr10.PE.haplotype.txt
********
BLOCK: offset: 803 len: 5 phased: 5
803 1 0
804 1 0
805 1 0
806 1 0
807 1 0
********
### HapCUT2:
/home/abj15/Research.Project/Run/HapCUT2/7.13.2019_826T_chr10.PE
BLOCK: offset: 803 len: 5 phased: 5 SPAN: 74 fragments 4
803 1 0 chr10 132858318 T G 0/1:99,0,12 0. 65.61
804 1 0 chr10 132858336 T C 0/1:50,0,38 0. 65.61
805 1 0 chr10 132858370 C T 0/1:38,0,30 0. 100.00
806 1 0 chr10 132858380 T A 0/1:44,0,16 0. 100.00
807 1 0 chr10 132858392 G T 0/1:40,0,43

## Slide 19: July23, 2019 Meeting To Do
Mix-SIH: sort chr10 data after considering “1” and “2”, then run it to compare with the previous (not sorting) results.
  Answer: Done.
  See files: MixSIH.corrected.input.sorted.and.compared.826T_ch10.PE.July24.2019
CSP:
  sort the fragment data,
  number genotype should be “1” (not 11), but not sure if it is the right way to prepare for the “population” genotype data
  about the genotype reformatting (e.g., “1/1”)may use “g” when using “sed”
  Answer: Done.
  See file: CSP.corrections.826T_chr10.PE.July24.2019
Process the NA12878 data (chr10) :
  Answer: Done. 2 attempts to align NA12878, appears to have issues
  *See files:
  NA12878.SRR9091899.sbatch.alignment.script.July24.2019 & sbatch.NA12878.alignment.July31.2019
Search the VCF data for NA12878 and parents (online or available software packages)
  Answer: Dataset_Searches.July31.2019
Look for simulated date for software packages & other real data Fosmid
  SDhaP – simulation data (HapMC-matlab data)- see if they have the truth or known haplotype
  Answer: Dataset_Searches.July31.2019
LEAP user guide:
https://itrcstats.itrc.txstate.edu/wiki/index.php/LEAP_Cluster_User_Guide

## Slide 20: July 31, 2019 to –do
Download NA12878:
Redownload using the “old” way (fastq_dump) 3 samples (hope no errors)
  Answer: Done.
  See files: fastq_dump_NA12878_NA12892.Aug5.2019 & ERRORS_fastq_dump.sbatch.NA12878.NA12891.NA12892.Aug1.2019 (NA12891 correctly downloaded)
download from a different resources (fastq file) using wget ftp files
  Answer: Done.
  See file: wget_NA12878_NA12891_NA12892_Aug7.2019
download the VCF files (record the hg version, hg18??)
  Answer: Done.
  See file: VCF.files_downloaded.Aug7.2019
Alignment:
remove “-I” (because it is not Illumina 1.3 or 1.5, it is ”Sanger” or Illumina 1.8+”),
set “-d 515000000”,
check the % of reads aligned (check total number of reads in SAM after removing the header, divided by the total number of reads 514,710,783
  Answer: Pending. Still running alignment sbatch scripts
  See: Alignment_Script folder in 56.Aug7.2019 zip file for all 7 alignment scripts
Meeting Notes:
discuss on the simulation data next time
CSP only gives 50% probability for the haplotype in each fragment may due to lack of data and/or small number of snps??
Next meeting: Aug 7 Wed 3:30 pm

## Slide 21: Aug 7, 2019 Notes by SS regarding NA12878 VCF download
Regarding download VCF: ftp://ftp-trace.ncbi.nih.gov/1000genomes/ftp/technical/working/20101201_cg_NA12878/
The “README.complete_genomics_NA12878_2010_12”:
This folder contains NA12878 data from Complete Genomics and the Broad from Hiseq and GA2 machines.
There is WGS data from CG, Hiseq and GA2 and Exome data from GA2.
The GA2 Exome bam was aligned to NCBI36 using Maq
The GA2 and Hiseq WGS bams were aligned to NCBI36 using BWA
All 3 of the bams were recalibrated using GATK. Both the raw and recalibrated bams can be found in this
directory
The fasta file they are aligned is also in this directory.
The CG bam was aligned by CG.
There are vcf files for snps and indels.
There are snps from Hiseq WGS and GA2 Exome data. These were called and filtered by GATK using current Broad
best practice.
There are snps and indels from CG data called by CG
Please look in the current.tree file at the root of the ftp site for md5sums

## Slide 22: Aug 7, 2019 to do
Next meeting: Aug 13 Tuesday 10 am
Update Key files
  Answer: Done.
  * See key_files folder
Download: fastdump for child and mother (a few runs, login.1 and login.2 or run at different times)
  Answer: successfully downloaded NA12892.mother, still getting persisting error message for NA12878
  * See download_and_comparison folder
Alignments: change time –t, -p himem, -mem=200GB for himem (not for shared)
  Answer: Aligned NA12891.father & NA12892.mother (10 million reads)
  *see Alignment folder
Software Package: Ran NA12891.father & NA12892.mother (wget & fastqdump 10million read chr10 aligned datasets) on HapCompass & HapCUT2
Notes:
(1) did not discusus simulation data(next tiem)
(2) May do some cleaning in the LEAP server after the download step is complete
(3) About downloading data notes, see file “Aug7.2019.txt” and the folder “Aug7.2019.NA12878.VCF”, this folder is saved in the Shared folder at tag212853 (SS MAC desktop) /Users/Shared/SS.file.for.abj15/Aug7.2019.NA12878.VCF